Strategic Institutional Plan 2010-2015

Action Plan

Vision Theme:			Reputation for Academic Excellence

Strategic Initiative:	Specialized programmatic accreditation obtained in business administration (AACSB—Association to Advance Collegiate Schools of Business).

Organizational Unit:		School of Business and Leadership

Desired Outcome/Goal:	Full AACSB International accreditation of Dominican University of California’s business programs achieved by end of AY 2014/15.

| Implementation Steps | Measure of Success | Timeline |  | Responsible Person Accountable, Responsible or Consulted |  | Incremental Resource Requirements |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Start | End |  |  |  |
| - Submit Business Pre-Eligibility Application. | Accepted to Pre-Accreditation Institution (precandidacy) status. | 6/2008 | 3/2009 | A/R C | Dean Institutional Research | Completed. |
| - Complete Accreditation Plan. | Accreditation Plan (candidacy status) accepted by AACSB. | 4/2009 | 5/2010 | A/R C | Dean Chief Academic Officer; SB&L Faculty | $14,500 for travel expenses of assigned Mentor; compensation for expert consultants to develop draft Plan; materials and supplies, etc. |
| - Recruit and appoint full-time faculty to comply with accreditation standards related to faculty sufficiency and qualifications (including scholarship productivity). | Successful recruiting of full-time doctorally qualified faculty in Management (2010); Accounting and Finance (2011); Accounting and Marketing (2012); MIS and International Business (2013); and International Finance (2014). | 10/2009 | 8/2014 | A/R C | Dean SB&L Faculty; Director of Human Resources | Annual costs of FT faculty, net after adjunct replacement and inclusive of normal annual salary increases: 2010/11: $118,000 2011/12: $186,810 2012/13: $182,151 2013/14: $214,258 2014/15: $41,970 Market/equity adjustments: 2010/11: $30,000, with normal annual salary increases |
| - Recruit and appoint an Associate Dean to augment SB&L staff in order to comply with accreditation standard on support. | Associate dean recruited and in residence. | 10/2009 | 7/2010 | A/R C | Dean SB&L Faculty; Director of Human Resources | $138,200/year, with normal annual salary increases |
| - Provide adequate office space and environment for new faculty and Associate Dean (e.g., renovated space in Bertrand Hall). | Satisfactory spaces available as new faculty/staff arrive. | 6/2010 | 8/2010 | A R C | Dean Director of Facilities Chief Academic Officer | $40,000 |
| - Prepare and submit Self-Evaluation Report to AACSB. | Completed Self-Evaluation Report accepted by AACSB. | 10/2010 | 6/2014 | A/R C | Dean SB&L Faculty; Institutional Research | $14,000 for AACSB Mentor travel, consultants, supplies and materials, etc. |
| - Host successful visit by AACSB Peer Review Team. | Full accreditation by AACSB. | TBD | 4/2015 | A/R C | Dean President; Chief Academic Officer | $11,000 for filing fees, Peer Review Team travel and expenses, etc. |

Assumptions:

External demands for the accountability of higher education institutions will continue, and the public will continue to view accreditation as an external standard of high academic quality and continuous improvement.  Internationally, Europe’s move to a uniform system of accounting for student learning outcomes will push the rest of the world to comply.  In the highly competitive field of business education, international students, corporations, and graduate business programs will continue to regard AACSB International accreditation as the gold standard for high quality.